## Master Project Schedule
MASTER PROJECT SCHEDULE TEMPLATE
| PROJECT TITLE |  | START DATE
| BlindGo |  | 2024-02-20 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
| Arleth Misuki O. Roque |  | 2024-05-09 |  |  | 80
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION | Complete |  | 2024-01-02 | 2024-02-09 | 39 |  | Not Started
1.1 | – Project Charter | Complete |  | 2024-01-02 | 2024-01-11 | 10 |  | In Progress
1.1.1 | –– Project Charter Revisions | Complete |  | 2024-01-07 | 2024-01-11 | 5 |  | Complete
1.2 | – Research | Complete |  | 2024-01-10 | 2024-02-23 | 45 |  | On Hold
1.3 | – Projections | Complete |  | 2024-01-10 | 2024-01-20 | 11
1.4 | – Stakeholders | Complete |  | 2024-01-16 | 2024-01-29 | 14
1.5 | – Guidelines | Complete |  | 2024-01-19 | 2024-02-01 | 14
1.6 | – Project Initiation | Complete |  | 2024-01-22 | 2024-02-09 | 19
2 | PROJECT DEFINITION AND PLANNING | Complete |  | 2024-01-28 | 2024-02-14 | 18
2.1 | – Scope & Goal Setting | Complete |  | 2024-01-28 | 2024-02-06 | 10
2.2 | – Budget | Complete |  | 2024-01-31 | 2024-02-02 | 3
2.3 | – Communication Plan | Complete |  | 2024-02-04 | 2024-02-12 | 9
2.4 | – Risk Management | Complete |  | 2024-02-06 | 2024-02-14 | 9
3 | PROJECT LAUNCH & EXECUTION | In Progress |  | 2024-02-18 | 2024-03-26 | 38
3.1 | – Status & Tracking | In Progress | Angel | 2024-02-18 | 2024-02-20 | 3
3.2 | – KPIs | In Progress |  | 2024-02-18 | 2024-02-23 | 6
3.2.1 | –– Monitoring | In Progress | Misuki | 2024-02-18 | 2024-02-26 | 9
3.2.2 | –– Forecasts | In Progress |  | 2024-02-21 | 2024-02-23 | 3
3.3 | – Project Updates | In Progress | Angel | 2024-02-22 | 2024-02-23 | 2
3.3.1 | –– Chart Updates | In Progress | Misuki | 2024-02-25 | 2024-03-26 | 31
4 | PROJECT PERFORMANCE / MONITORING | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4.1 | – Project Objectives | In Progress |  | 2024-02-25 | 2024-02-28 | 4
4.2 | – Quality Deliverables | On Hold |  | 2024-02-26 | 2024-03-03 | 7
4.3 | – Effort & Cost Tracking | Not Started |  | 2024-02-25 | 2024-03-06 | 11
4.4 | – Project Performance | Not Started | Jasso | 2024-03-03 | 2024-03-26 | 24

## BLANK - Master Project Schedule
MASTER PROJECT SCHEDULE
| PROJECT TITLE |  | START DATE
| BlindGo |  | 2025-02-20 |  |  | PROJECT DURATION
| PROJECT MANAGER |  |  |  |  | in days
| Arleth Misuki O. Roque |  | 2025-05-09 |  |  | 79
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION | Complete |  | 2025-02-20 | 2025-02-23 | 4 |  | Not Started
1.1 | – Project Charter | Complete | Misuki | 2025-02-20 | 2025-02-20 | 1 |  | In Progress
1.1.1 | –– Project Charter Revisions | Complete | Misuki | 2025-02-20 | 2025-02-20 | 1 |  | Complete
1.2 | – Research | Complete | Angel | 2025-02-21 | 2025-02-21 | 1 |  | On Hold
1.3 | – Projections | Complete | Angel | 2025-02-21 | 2025-02-21 | 1
1.4 | – Stakeholders | Complete | Jasso | 2025-02-22 | 2025-02-22 | 1
1.5 | – Guidelines | Complete | Jasso | 2025-02-22 | 2025-02-22 | 1
1.6 | – Project Initiation | Complete | Angel | 2025-02-23 | 2025-02-23 | 1
2 | PROJECT DEFINITION AND PLANNING | Complete |  | 2025-02-23 | 2025-02-26 | 4
2.1 | – Scope & Goal Setting | Complete | Jasso | 2025-02-23 | 2025-02-23 | 1
2.2 | – Budget | Complete | Misuki | 2025-02-24 | 2025-02-24 | 1
2.3 | – Communication Plan | Complete | Jasso | 2025-02-25 | 2025-02-25 | 1
2.4 | – Risk Management | Complete | Angel | 2025-02-26 | 2025-02-26 | 1
3 | PROJECT LAUNCH & EXECUTION | In Progress |  | 2025-02-26 | 2025-03-17 | 20
3.1 | – Status & Tracking | In Progress | Angel | 2025-02-26 | 2025-02-26 | 1
3.2 | – GPS Implementation | In Progress | Jasso | 2025-03-03 | 2025-03-04 | 2
3.2.1 | –– Monitoring | In Progress | Misuki | 2025-03-04 | 2025-03-05 | 2
3.2.2 | –– Data Extraction | In Progress | Misuki | 2025-03-06 | 2025-03-07 | 2
3.3 | – Arduino Cloud To Backend | In Progress | Jasso, Angel | 2025-03-07 | 2025-03-12 | 6
3.3.1 | – Coordinates | In Progress | Angel | 2025-03-12 | 2025-03-17 | 6
4 | PROJECT PERFORMANCE / MONITORING | On Hold |  | 2025-03-18 | 2025-05-09 | 53
4.1 | – Testing | On Hold | Misuki | 2025-03-18 | 2025-04-06 | 20
4.2 | – Monitoring Behavior | On Hold | Jasso | 2025-04-06 | 2025-04-25 | 20
4.4 | – Project Performance | On Hold | Angel | 2025-04-25 | 2025-05-09 | 15
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.